## Ark1
Week | Start Data | Notes | Risk | Writing
1 | 2020-08-31 | Project plan, initial models on MNIST, litterature study | 1
2 | 2020-09-07 | Litterature study | 1 | Introduction
3 | 2020-09-14 | Litterature study | 1
4 | 2020-09-21 | Litterature study | 1 | Previous work
5 | 2020-09-28 | Create and test improved model for MNIST | 3
6 | 2020-10-05 | Create and test improved model for MNIST | 3
7 | 2020-10-12 | Writing | 3 | Method and results for MNIST
8 | 2020-10-19 | Find new data set and establish baseline / state-of-the-art | 3
9 | 2020-10-26 | Develop and test model for new data set | 5
10 | 2020-11-02 | Develop and test model for new data set | 5
11 | 2020-11-09 | Develop and test model for new data set | 5
12 | 2020-11-16 | Develop and test model for new data set | 5
13 | 2020-11-23 | Develop and test model for new data set | 5
14 | 2020-11-30 | Develop and test model for new data set | 5
15 | 2020-12-07 | Develop and test model for new data set | 5
16 | 2020-12-14 | Writing | 2
17 | 2020-12-21 | Writing | 2 | Method for new data
18 | 2020-12-28 | Writing | 2
19 | 2021-01-04 | Writing | 2 | Results
20 | 2021-01-11 | Writing | 2 | Discussion and future work
21 | 2021-01-18 | Corrections | 1 | Conclussion
22 | 2021-01-25 | Corrections | 1 | Abstract
Formulas:
Start Data = [Start Data, row above]+7